## README
Capital Project Submission QA & Weekly Executive Report
Recreated work sample - Brystal Pearson, CAPM - ALL DATA IS SYNTHETIC
What this is | A rebuilt version of work I did as a contract Project Analyst on a multi-region healthcare capital portfolio: routing invoices, POs, and commitment changes for approval, finding why submissions kept getting rejected, fixing it with a standardized pre-submission checklist, and reporting budget position to leadership weekly.
Data | Every project, person, amount, and date is invented. Rejection categories are modeled on the kinds of issues I saw; no client records, files, or screenshots are included.
The story in one line | I stopped fixing rejected submissions one at a time and fixed the template they were built from.
Tab | Purpose
Submission_Log | 96 synthetic submissions over 12 weeks. Weeks 1-6 = before the checklist; weeks 7-12 = after.
Rejection_Pareto | Rejections by reason, before vs. after, with cumulative % - the analysis that pointed to the fix.
PreSubmit_Checklist | The standardized checklist. Each item is tied to the rejection reason it prevents.
Budget_Status | 12 capital projects: approved budget, committed, invoiced, remaining, closeout date, and an automatic flag.
Weekly_Exec_Report | One-page leadership summary. Change the report date (gray cell) and every figure recalculates.
Legend | Gray-filled cells are inputs you can edit. Everything else is a formula or synthetic source data.
Note on results | Before/after figures here come from synthetic data and illustrate the method. They are not measured outcomes from the engagement.

## Weekly_Exec_Report
Weekly Executive Report - Capital Portfolio
Synthetic data. One page, decision-ready.
Report date |  | 2025-11-21
Report week |  | 12 | Week 1 starts 09/01/2025; capped at week 12 (end of sample data).
1. BUDGET POSITION
Measure |  | Value
Approved budget |  | 14010000
Committed |  | 12072000
Invoiced to date |  | 9569000
Uncommitted budget |  | 1938000
% of budget committed |  | 86.17%
2. SUBMISSION QUALITY
Measure | Before checklist (wk 1-6) | After checklist (wk 7-12) | This week
Submissions | 48 | 48 | 8
Rejected on first pass | 22 | 5 | 0
First-pass approval rate | 54.17% | 89.58% | 100%
Avg days to final approval | 6.9167 | 4.3958 | 3.25
Top rejection reason before checklist: |  | Cost code missing or not on approved budget line
Top rejection reason after checklist: |  | Amount exceeds remaining commitment balance
3. PROJECTS NEEDING ATTENTION
Flagged projects: |  | 4
Project ID | Project | Owner | Flag | Open Commitment ($)
CP-2401 | Central - OR Renovation | J. Alvarez | - | 123000
CP-2402 | East - Imaging Suite | K. Brooks | - | 582000
CP-2403 | West - HVAC Replacement | S. Patel | - | 293000
CP-2404 | Central - ED Expansion | D. Okafor | Over 95% committed | 472000
CP-2405 | East - Roof Replacement | J. Alvarez | - | 356000
CP-2406 | West - Pharmacy Upgrade | J. Alvarez | - | 82000
CP-2407 | Central - Generator Install | S. Patel | Closeout overdue | 23000
CP-2408 | East - Lab Remodel | K. Brooks | Over 95% committed | 149000
CP-2409 | West - Parking Structure | K. Brooks | - | 132000
CP-2410 | Central - Patient Tower Refresh | M. Chen | Closeout overdue | 102000
CP-2411 | East - Sterile Processing | S. Patel | - | 0
CP-2412 | West - Clinic Build-Out | M. Chen | - | 189000
4. DECISIONS / ASKS FOR LEADERSHIP
1. Approve a quarterly budget-line refresh so R2 (over remaining balance) stops recurring.
2. Publish an approver routing matrix by amount and region to close out R5.
3. Confirm owners and revised dates for every project flagged 'Closeout overdue'.

## Submission_Log
Submission Log
Synthetic. Checklist introduced at week 7.
Submission ID | Week | Submitted | Project ID | Doc Type | Amount ($) | Submitted By | Checklist Used | First-Pass Outcome | Rejection Reason | Resubmissions | Days to Final Approval
S-1001 | 1 | 2025-09-02 | CP-2411 | Commitment Change | 42700 | J. Alvarez | No | Rejected | Required backup missing (signed pay app, lien waiver) | 1 | 6
S-1002 | 1 | 2025-09-02 | CP-2406 | PO | 51100 | D. Okafor | No | Rejected | Retainage or math error | 1 | 11
S-1003 | 1 | 2025-09-03 | CP-2407 | PO | 29100 | S. Patel | No | Rejected | Required backup missing (signed pay app, lien waiver) | 1 | 14
S-1004 | 1 | 2025-09-04 | CP-2407 | Commitment Change | 74300 | J. Alvarez | No | Rejected | Retainage or math error | 1 | 14
S-1005 | 1 | 2025-09-04 | CP-2401 | Invoice | 30900 | D. Okafor | No | Rejected | PO number missing or does not match commitment | 1 | 7
S-1006 | 1 | 2025-09-01 | CP-2410 | PO | 97100 | S. Patel | No | Approved |  | 0 | 2
S-1007 | 1 | 2025-09-01 | CP-2405 | Invoice | 23600 | M. Chen | No | Approved |  | 0 | 5
S-1008 | 1 | 2025-09-05 | CP-2409 | Invoice | 93400 | K. Brooks | No | Rejected | PO number missing or does not match commitment | 1 | 14
S-1009 | 2 | 2025-09-12 | CP-2403 | Invoice | 138200 | M. Chen | No | Approved |  | 0 | 2
S-1010 | 2 | 2025-09-09 | CP-2408 | Invoice | 23700 | J. Alvarez | No | Approved |  | 0 | 4
S-1011 | 2 | 2025-09-12 | CP-2404 | Commitment Change | 170700 | K. Brooks | No | Rejected | Amount exceeds remaining commitment balance | 1 | 7
S-1012 | 2 | 2025-09-09 | CP-2403 | PO | 170600 | S. Patel | No | Rejected | Amount exceeds remaining commitment balance | 1 | 12
S-1013 | 2 | 2025-09-11 | CP-2404 | Invoice | 74200 | S. Patel | No | Approved |  | 0 | 4
S-1014 | 2 | 2025-09-09 | CP-2408 | Invoice | 47600 | S. Patel | No | Rejected | Cost code missing or not on approved budget line | 1 | 14
S-1015 | 2 | 2025-09-08 | CP-2404 | Invoice | 16500 | J. Alvarez | No | Approved |  | 0 | 3
S-1016 | 2 | 2025-09-09 | CP-2406 | Invoice | 94500 | S. Patel | No | Rejected | Amount exceeds remaining commitment balance | 1 | 14
S-1017 | 3 | 2025-09-16 | CP-2410 | PO | 46800 | J. Alvarez | No | Approved |  | 0 | 5
S-1018 | 3 | 2025-09-15 | CP-2402 | PO | 66400 | J. Alvarez | No | Approved |  | 0 | 2
S-1019 | 3 | 2025-09-18 | CP-2407 | Invoice | 144900 | K. Brooks | No | Rejected | Cost code missing or not on approved budget line | 1 | 14
S-1020 | 3 | 2025-09-19 | CP-2407 | Invoice | 53000 | J. Alvarez | No | Rejected | Routed to wrong approver | 1 | 13
S-1021 | 3 | 2025-09-16 | CP-2401 | Commitment Change | 151100 | D. Okafor | No | Approved |  | 0 | 3
S-1022 | 3 | 2025-09-16 | CP-2408 | PO | 41600 | D. Okafor | No | Approved |  | 0 | 2
S-1023 | 3 | 2025-09-17 | CP-2401 | PO | 50700 | D. Okafor | No | Approved |  | 0 | 5
S-1024 | 3 | 2025-09-15 | CP-2409 | PO | 31200 | M. Chen | No | Rejected | Retainage or math error | 1 | 14
S-1025 | 4 | 2025-09-22 | CP-2401 | Invoice | 106800 | S. Patel | No | Approved |  | 0 | 3
S-1026 | 4 | 2025-09-22 | CP-2402 | Invoice | 16100 | S. Patel | No | Rejected | Routed to wrong approver | 1 | 12
S-1027 | 4 | 2025-09-26 | CP-2404 | Commitment Change | 108600 | S. Patel | No | Approved |  | 0 | 5
S-1028 | 4 | 2025-09-24 | CP-2409 | Invoice | 168500 | D. Okafor | No | Rejected | PO number missing or does not match commitment | 1 | 9
S-1029 | 4 | 2025-09-22 | CP-2403 | Invoice | 84500 | D. Okafor | No | Approved |  | 0 | 2
S-1030 | 4 | 2025-09-23 | CP-2410 | Commitment Change | 179300 | M. Chen | No | Rejected | Cost code missing or not on approved budget line | 1 | 10
S-1031 | 4 | 2025-09-26 | CP-2402 | Invoice | 69000 | S. Patel | No | Rejected | Required backup missing (signed pay app, lien waiver) | 1 | 10
S-1032 | 4 | 2025-09-24 | CP-2401 | Commitment Change | 56700 | J. Alvarez | No | Approved |  | 0 | 3
S-1033 | 5 | 2025-09-30 | CP-2402 | Commitment Change | 31400 | M. Chen | No | Rejected | Cost code missing or not on approved budget line | 1 | 11
S-1034 | 5 | 2025-09-29 | CP-2409 | PO | 48200 | D. Okafor | No | Approved |  | 0 | 2
S-1035 | 5 | 2025-09-30 | CP-2405 | Invoice | 4600 | D. Okafor | No | Approved |  | 0 | 4
S-1036 | 5 | 2025-10-03 | CP-2409 | PO | 102700 | J. Alvarez | No | Rejected | Retainage or math error | 1 | 8
S-1037 | 5 | 2025-10-01 | CP-2406 | Commitment Change | 101200 | M. Chen | No | Approved |  | 0 | 2
S-1038 | 5 | 2025-10-02 | CP-2401 | Invoice | 41000 | S. Patel | No | Rejected | Cost code missing or not on approved budget line | 1 | 14
S-1039 | 5 | 2025-10-02 | CP-2403 | Invoice | 156200 | J. Alvarez | No | Approved |  | 0 | 3
S-1040 | 5 | 2025-10-01 | CP-2403 | Invoice | 141700 | K. Brooks | No | Approved |  | 0 | 3
S-1041 | 6 | 2025-10-07 | CP-2402 | PO | 157500 | D. Okafor | No | Approved |  | 0 | 3
S-1042 | 6 | 2025-10-06 | CP-2406 | Invoice | 148400 | K. Brooks | No | Approved |  | 0 | 3
S-1043 | 6 | 2025-10-10 | CP-2407 | Invoice | 53000 | D. Okafor | No | Rejected | Required backup missing (signed pay app, lien waiver) | 1 | 11
S-1044 | 6 | 2025-10-07 | CP-2411 | Commitment Change | 62300 | S. Patel | No | Rejected | Routed to wrong approver | 1 | 10
S-1045 | 6 | 2025-10-09 | CP-2405 | Invoice | 23100 | S. Patel | No | Approved |  | 0 | 4
S-1046 | 6 | 2025-10-06 | CP-2409 | Invoice | 71800 | D. Okafor | No | Approved |  | 0 | 4
S-1047 | 6 | 2025-10-08 | CP-2401 | Commitment Change | 166900 | D. Okafor | No | Approved |  | 0 | 3
S-1048 | 6 | 2025-10-08 | CP-2402 | Invoice | 113700 | S. Patel | No | Approved |  | 0 | 2
S-1049 | 7 | 2025-10-14 | CP-2405 | PO | 61400 | D. Okafor | Yes | Approved |  | 0 | 3
S-1050 | 7 | 2025-10-16 | CP-2411 | PO | 123200 | S. Patel | Yes | Approved |  | 0 | 4
S-1051 | 7 | 2025-10-16 | CP-2401 | Invoice | 54500 | D. Okafor | Yes | Approved |  | 0 | 4
S-1052 | 7 | 2025-10-13 | CP-2408 | Invoice | 94000 | M. Chen | Yes | Approved |  | 0 | 3
S-1053 | 7 | 2025-10-15 | CP-2409 | Commitment Change | 63000 | K. Brooks | Yes | Approved |  | 0 | 3
S-1054 | 7 | 2025-10-17 | CP-2404 | Invoice | 8300 | J. Alvarez | Yes | Approved |  | 0 | 5
S-1055 | 7 | 2025-10-16 | CP-2408 | PO | 160000 | D. Okafor | Yes | Approved |  | 0 | 5
S-1056 | 7 | 2025-10-16 | CP-2404 | Invoice | 119500 | K. Brooks | Yes | Rejected | Routed to wrong approver | 1 | 7
S-1057 | 8 | 2025-10-23 | CP-2403 | Commitment Change | 85800 | K. Brooks | Yes | Approved |  | 0 | 2
S-1058 | 8 | 2025-10-24 | CP-2408 | Commitment Change | 177900 | S. Patel | Yes | Approved |  | 0 | 5
S-1059 | 8 | 2025-10-23 | CP-2407 | Commitment Change | 82500 | M. Chen | Yes | Approved |  | 0 | 5
S-1060 | 8 | 2025-10-22 | CP-2404 | Invoice | 138800 | D. Okafor | Yes | Approved |  | 0 | 3
S-1061 | 8 | 2025-10-21 | CP-2402 | Invoice | 45300 | K. Brooks | Yes | Approved |  | 0 | 2
S-1062 | 8 | 2025-10-23 | CP-2404 | PO | 126100 | D. Okafor | Yes | Approved |  | 0 | 2
S-1063 | 8 | 2025-10-24 | CP-2406 | Commitment Change | 86000 | J. Alvarez | Yes | Rejected | Routed to wrong approver | 1 | 12
S-1064 | 8 | 2025-10-23 | CP-2410 | PO | 87900 | D. Okafor | Yes | Approved |  | 0 | 4
S-1065 | 9 | 2025-10-28 | CP-2409 | Commitment Change | 144800 | M. Chen | Yes | Approved |  | 0 | 5
S-1066 | 9 | 2025-10-28 | CP-2407 | PO | 9100 | D. Okafor | Yes | Approved |  | 0 | 5
S-1067 | 9 | 2025-10-27 | CP-2403 | Commitment Change | 98000 | D. Okafor | Yes | Approved |  | 0 | 2
S-1068 | 9 | 2025-10-28 | CP-2403 | PO | 36000 | D. Okafor | Yes | Approved |  | 0 | 4
S-1069 | 9 | 2025-10-29 | CP-2406 | Invoice | 138000 | J. Alvarez | Yes | Approved |  | 0 | 5
S-1070 | 9 | 2025-10-27 | CP-2408 | Invoice | 135800 | J. Alvarez | Yes | Rejected | Retainage or math error | 1 | 9
S-1071 | 9 | 2025-10-30 | CP-2401 | Invoice | 39100 | J. Alvarez | Yes | Rejected | Amount exceeds remaining commitment balance | 1 | 8
S-1072 | 9 | 2025-10-28 | CP-2410 | Invoice | 85800 | S. Patel | Yes | Approved |  | 0 | 4
S-1073 | 10 | 2025-11-03 | CP-2410 | Invoice | 140900 | S. Patel | Yes | Approved |  | 0 | 4
S-1074 | 10 | 2025-11-06 | CP-2401 | Invoice | 105300 | K. Brooks | Yes | Approved |  | 0 | 5
S-1075 | 10 | 2025-11-05 | CP-2402 | Commitment Change | 125500 | S. Patel | Yes | Approved |  | 0 | 2
S-1076 | 10 | 2025-11-05 | CP-2402 | Commitment Change | 141700 | J. Alvarez | Yes | Approved |  | 0 | 5
S-1077 | 10 | 2025-11-03 | CP-2409 | Invoice | 6200 | D. Okafor | Yes | Approved |  | 0 | 5
S-1078 | 10 | 2025-11-07 | CP-2406 | PO | 128500 | S. Patel | Yes | Approved |  | 0 | 4
S-1079 | 10 | 2025-11-05 | CP-2408 | PO | 80700 | K. Brooks | Yes | Approved |  | 0 | 4
S-1080 | 10 | 2025-11-07 | CP-2402 | Invoice | 159200 | S. Patel | Yes | Approved |  | 0 | 5
S-1081 | 11 | 2025-11-11 | CP-2411 | PO | 63200 | D. Okafor | Yes | Approved |  | 0 | 4
S-1082 | 11 | 2025-11-14 | CP-2404 | Invoice | 144400 | J. Alvarez | Yes | Approved |  | 0 | 4
S-1083 | 11 | 2025-11-14 | CP-2409 | Invoice | 19100 | K. Brooks | Yes | Approved |  | 0 | 5
S-1084 | 11 | 2025-11-11 | CP-2408 | PO | 82900 | M. Chen | Yes | Rejected | Amount exceeds remaining commitment balance | 1 | 12
S-1085 | 11 | 2025-11-13 | CP-2411 | Commitment Change | 68900 | S. Patel | Yes | Approved |  | 0 | 4
S-1086 | 11 | 2025-11-11 | CP-2406 | Invoice | 127700 | J. Alvarez | Yes | Approved |  | 0 | 4
S-1087 | 11 | 2025-11-11 | CP-2404 | Invoice | 25000 | K. Brooks | Yes | Approved |  | 0 | 3
S-1088 | 11 | 2025-11-10 | CP-2408 | Invoice | 131500 | K. Brooks | Yes | Approved |  | 0 | 4
S-1089 | 12 | 2025-11-19 | CP-2405 | Invoice | 67500 | J. Alvarez | Yes | Approved |  | 0 | 3
S-1090 | 12 | 2025-11-17 | CP-2401 | Commitment Change | 55400 | J. Alvarez | Yes | Approved |  | 0 | 5
S-1091 | 12 | 2025-11-17 | CP-2410 | Invoice | 86600 | M. Chen | Yes | Approved |  | 0 | 3
S-1092 | 12 | 2025-11-21 | CP-2408 | Invoice | 148700 | J. Alvarez | Yes | Approved |  | 0 | 2
S-1093 | 12 | 2025-11-18 | CP-2403 | Invoice | 146800 | J. Alvarez | Yes | Approved |  | 0 | 2
S-1094 | 12 | 2025-11-21 | CP-2409 | PO | 110700 | D. Okafor | Yes | Approved |  | 0 | 3
S-1095 | 12 | 2025-11-19 | CP-2408 | PO | 56300 | S. Patel | Yes | Approved |  | 0 | 5
S-1096 | 12 | 2025-11-18 | CP-2410 | Invoice | 111300 | M. Chen | Yes | Approved |  | 0 | 3

## Rejection_Pareto
Rejection Pareto - Before vs. After Checklist
Before = weeks 1-6 (no checklist). After = weeks 7-12.
Code | Rejection Reason | Before | % of Before | Cumulative % (Before) | After | Change
R1 | Cost code missing or not on approved budget line | 5 | 22.73% | 22.73% | 0 | -5
R4 | Required backup missing (signed pay app, lien waiver) | 4 | 18.18% | 40.91% | 0 | -4
R6 | Retainage or math error | 4 | 18.18% | 59.09% | 1 | -3
R2 | Amount exceeds remaining commitment balance | 3 | 13.64% | 72.73% | 2 | -1
R3 | PO number missing or does not match commitment | 3 | 13.64% | 86.36% | 0 | -3
R5 | Routed to wrong approver | 3 | 13.64% | 100% | 2 | -1
| Total rejections | 22 |  |  | 5 | -17
Read it this way:
The top three reasons by count were preventable before submission - they were template problems, not people problems. That is what the checklist targets.
R2 and R5 persist after: budget balance and approver changes happen upstream, so they need a budget refresh and a routing matrix, not just a checklist.

## PreSubmit_Checklist
Pre-Submission Checklist
Completed by the submitter before routing. Analyst confirms before it moves forward.
# | Check | How to verify | Prevents | Done (Y/N)
1 | Cost code matches an approved budget line | Compare to current budget line list for the project | R1 | Y
2 | Amount is within the remaining commitment balance | Remaining = commitment - invoiced to date; pull from Budget_Status | R2
3 | PO number present and matches the commitment | Match PO on document to commitment record | R3
4 | Signed pay application attached | Contractor and architect signatures present | R4
5 | Conditional lien waiver attached for this period | Period and amount match the pay application | R4
6 | Approver matches the routing matrix for this amount and region | Check threshold tier before routing | R5
7 | Retainage calculated at contract rate | Recalculate; line totals tie to the summary | R6
8 | Document type and project ID are correct | Matches project record exactly | R1
| Items complete |  |  | 1 of 8
| Ready to route? |  |  | NO - hold
Example row: enter Y or N in the gray cells. All eight must be Y before a submission routes.

## Budget_Status
Capital Project Budget Status
Synthetic. Amounts in dollars.
Report date: | 2025-11-21
Project ID | Project | Region | Owner | Approved Budget ($) | Committed ($) | Invoiced to Date ($) | Uncommitted Budget ($) | Open Commitment ($) | % Committed | Status | Target Closeout | Flag
CP-2401 | Central - OR Renovation | Central | J. Alvarez | 480000 | 377000 | 254000 | 103000 | 123000 | 78.54% | Active | 2026-01-20
CP-2402 | East - Imaging Suite | East | K. Brooks | 2800000 | 2238000 | 1656000 | 562000 | 582000 | 79.93% | Active | 2026-01-08
CP-2403 | West - HVAC Replacement | West | S. Patel | 750000 | 668000 | 375000 | 82000 | 293000 | 89.07% | Active | 2026-05-31
CP-2404 | Central - ED Expansion | Central | D. Okafor | 1500000 | 1485000 | 1013000 | 15000 | 472000 | 99% | Active | 2026-01-25 | Over 95% committed
CP-2405 | East - Roof Replacement | East | J. Alvarez | 1200000 | 1009000 | 653000 | 191000 | 356000 | 84.08% | Active | 2026-01-11
CP-2406 | West - Pharmacy Upgrade | West | J. Alvarez | 1500000 | 1202000 | 1120000 | 298000 | 82000 | 80.13% | Closeout | 2026-02-21
CP-2407 | Central - Generator Install | Central | S. Patel | 2100000 | 1886000 | 1863000 | 214000 | 23000 | 89.81% | Closeout | 2025-10-11 | Closeout overdue
CP-2408 | East - Lab Remodel | East | K. Brooks | 900000 | 866000 | 717000 | 34000 | 149000 | 96.22% | Active | 2026-05-12 | Over 95% committed
CP-2409 | West - Parking Structure | West | K. Brooks | 480000 | 379000 | 247000 | 101000 | 132000 | 78.96% | Active | 2026-01-05
CP-2410 | Central - Patient Tower Refresh | Central | M. Chen | 480000 | 415000 | 313000 | 65000 | 102000 | 86.46% | Closeout | 2025-11-03 | Closeout overdue
CP-2411 | East - Sterile Processing | East | S. Patel | 1200000 | 991000 | 991000 | 209000 | 0 | 82.58% | Closed | 2025-11-07
CP-2412 | West - Clinic Build-Out | West | M. Chen | 620000 | 556000 | 367000 | 64000 | 189000 | 89.68% | Closeout | 2026-03-23
| Portfolio total |  |  | 14010000 | 12072000 | 9569000 | 1938000 | 2503000 | 86.17%